## Slide 1
naneNamed
KOICA
Korea International Cooperation Agency
Implementation of a Volume-Based Waste Fee System in Sri Lanka
Action Plan
-Title of the KOICA fellowship program
액션플랜 예시
Name :

## Slide 2
Background and Purpose
Current Status and Issues
Improvement Strategy
Specific Action Plan
Expected Results
Contents

## Slide 3
Background and Purpose
Background
Purpose
In Sri Lanka, due to economic development and rising living standards, the volume of municipal solid waste (MSW) has increased rapidly, and the quality of waste has become more complicated and complex to dispose of.
In the absence of an efficient waste management system, over 80% of 7,000 tons of unsegregated MSW are being sent to dump sites every day.
To implement a Volume-Based Waste Fee System with a definite target
to minimize waste generation and increase recycling in three identified
local authorities in the Western Province.

## Slide 4
Current Status and Issues
National Policy on Solid Waste Management prepared by the Ministry of Environment proclaimed that maximum opportunities for the application of the 3R concepts (reduce, reuse, and recycle) should be provided.
Western Provincial Council enacted the Municipal Solid Waste Management Rules in 2008 to govern municipal solid waste management based on the policy principles of 3R.
National Policy and Western Provincial Rules have not been fully satisfactorily enforced.
This is largely attributable to the absence of an efficiently functioning waste management system in Sri Lanka.
Possible only through satisfactory implementation of the 3R policy measures which are primarily based on sound accomplishment of source segregation.
Current Status and Issues

## Slide 5
Current Status and Issues – Gap Analysis
Proposed Overall Goals (Objectives)
Proposed Purpose
Implement the 3R Policy
Implement Volume-Based Waste Fee System
Accomplish source segregation
Prepare waste management guidelines
To Be
As Is
Minimize waste generation
Increase recycling in target areas
Promote “Resource Re-Circulated Society”
Quality of waste complicated to dispose of
Absence of efficient waste management system
80% of 7,000 tons of unsegregated MSW
Increase in volume of Municipal Solid Waste

## Slide 6
Improvement Strategy
Improvement Strategy
Implementation of Volume-Based Waste Fee System
Implementation of the 3R policy
System evolved which normally adopted economic
Incentives based on
The polluter-pays principle
3R
Reduce
Reuse
Recycle

## Slide 7
Benefits
Reduce the volume of municipal solid waste headed to landfills and incinerators
Provide a large increase in recycling volumes
Increase citizen participation in recycling and composting activities through segregation
Increase flexibility, efficiency and cost effectiveness in waste management
  Increase in illegal dumping
  → Can be minimized by enforcement activities by Environmental Unit in every police station
  Illegal VBWF bag production
  → Can be minimized if Korean VBWF bags are used initially for the program.
Improvement Strategy
Risks

## Slide 8
Specific Action Plan
Specific Action Plan and Activities
    Purchase equipment and vehicles appropriate to the program
    Obtain VBW bags for mixed waste and non-recyclable wastes from KOICA to provide to households and other discharges
Providing bags and bins for recyclables and perishables
Implement the program in 40% of the individual local authority area within six (6) months
    Preparation of VBWF Guidelines for local conditions on classification of wastes, the type/size/price/material/technical specifications of VBWB bags, collection frequency, monitoring of illegal disposals, etc.

## Slide 9
Action Plan
The steps to achieve the Action Plan’s goals
STEP 1
Minimize mixed waste handling
STEP 2
Develop the concept of “Resource Re-Circulated Society”
STEP 3
Expand the lifetime of existing landfill sites
Promote segregation of waste
Meet the recurrent expenses of the LAs for the MSW program through sales of VBWF bags
Replicate the program in other 45 local authorities of the province and thereafter the other 287 local authorities of Sri Lanka

## Slide 10
Implementing Organization
  Name of the organization: Waste Management Authority
  Nature or type of the organization: Provincial Authority established under the Provincial Waste Management Statute of No.01 of 1999
  Major functions of the organization: Facilitation and regulation of local authorities of the Western Province for the management of their wastes.
Duration of the Project : 1 Year
- Date of commencement : 2013.05.13
- Date of completion : 2014.05.01
Outline of the Action Plan

## Slide 11
Action Plan Time Table
Duration: (1 Year) First Year Work Plan: 2013
No | Item | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | Purchase equipment and vehicles appropriate to the program |  |  |  |  |  |  |  |  |  |  |  | 
2 | Obtain VBW bags from Korea |  |  |  |  |  |  |  |  |  |  |  | 
3 | Awareness of local governments, police and people of the area |  |  |  |  |  |  |  |  |  |  |  | 
4 | Implementation of the program in 40% of individual local authority area |  |  |  |  |  |  |  |  |  |  |  | 
5 | Implementation of the program in 100% of individual local authority area |  |  |  |  |  |  |  |  |  |  |  | 
6 | Monitor, evaluate and report the outcome to all stakeholder agencies |  |  |  |  |  |  |  |  |  |  |  | 
7 | Preparation of VBWF Guidelines for local conditions |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 12
Outline of the Action Plan–Budget (if needed)
Activity | TOTAL | First Year (Cost US$) | Responsibility
Awareness | 5000 | 5000 | Provincial and Local Governments
Domestic Fund(in kind) | 100,000 | 100,000 | Provincial and Local Governments
Foreign Fund (Korea) | 15,000 | 15,000 | KOICA through Government of Korea
TOTAL AMOUNT | 120,000 | 120,000 | -

## Slide 13
Expected Results – Outputs/Outcomes
Economic Effects
Present direct expenses for local governments will be reduced.
The drastic decrease in sales of segregated recyclables could be effectively utilized
for better management of MSW in the respective local community.
Technical Effects
Korea’s experiences and technology for the implementation of the VBW Fee and the usage of waste as a “resource” could be introduced.
Various recycling technologies that utilize recyclable waste to be segregated in great
volumes for industrial purposes will be introduced to the country.
Social and Environmental Effects
There will be a significant greenhouse gas emission reduction due to less dumping and burning of waste.
Vector-borne and pandemic diseases due to improper waste management will be reduced.
Changes in the behaviors and thinking pattern of the people will create a new social lifestyle in the country.

## Slide 14
Thank you!